## Tabelle1
Sprint Review Protocol
Sprint No: |  | 3
Date & Time |  | 2022-12-06
Group Number |  | 18
Participant 1 |  | Shahan Karigian
Participant 2 |  | Maximilian Turza
Participant 3 |  | Israel Tschilumba
Participant 4 |  | Deyaa Yousef
Participant 5 |  | Seunghyun Hwang
Mentor |  | Gerd Holweg
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
4 | Interview Frau Dregely | 4 | 4 | 0
22 | Interview Dregely Ergebnisse auswerten | 2 | 3 | 1
19 | Angular Projekt aufsetzen | 4 | 2 | -2
4 |  |  |  | 0
5 |  |  |  | 0
6 |  |  |  | 0
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | -1 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol